## Overview
MAIS-MVP Technical Review — Issues, Roadmap & Backlog
Review date: 2026-07-06 · Scope: full repository + live-site spot check · Companion: TECHNICAL-REVIEW.md / .docx
Sheet | Contents
Issues Register | 18 major issues with severity, evidence, risk, fix, effort, owner, priority
Roadmap | 3-month recovery plan in 4 phases with success criteria
Backlog | 24 engineering tickets with acceptance criteria (BK-01…BK-24)
Readiness Checklist | Minimum production-readiness bar before real classrooms
Issue counts by severity
Critical | 5
High | 8
Medium | 5
Total issues | 18
Backlog tickets by priority
P0 | 7
P1 | 6
P2 | 6
P3 | 5
Total tickets | 24

## Issues Register
ID | Issue title | Severity | Area | Evidence / likely symptom | Why it matters | Risk if ignored | Recommended fix | Effort | Suggested owner | Priority (next 3 months) | Related tickets
ISS-01 | Entire platform state stored as a single JSON blob (app_state row) | Critical | Data / Architecture | lib/server/userStore.ts: all domains serialized into one app_state row; every mutation runs SELECT…FOR UPDATE on that row, rewrites the full payload and re-syncs 22 projection_* tables; local dev blob is 77 MB (SQLite + 117 MB WAL). | Global write lock = a handful of concurrent users max; every read loads the full platform state into memory; write amplification on every keystroke-level action. | Site freezes/timeouts with the first real classroom; one bad write or normalize bug corrupts ALL data; costs grow with every user action. | Freeze the blob (no new data), then strangler-migrate domain by domain to normalized tables — the pattern already proven by hot-auth + practice_attempts fast paths. | L | Senior + junior | Months 1–3 (top priority) | BK-07, BK-11, BK-12
ISS-02 | No database migration framework or schema versioning | Critical | Data | No migrations directory; runtime CREATE TABLE IF NOT EXISTS / ALTER TABLE calls inside userStore.ts; schemaVersion constant = 1. | Schema evolution is untracked, unrepeatable and irreversible; staging and prod can silently diverge. | A failed deploy mid-schema-change leaves prod in an unknown state with no down-path. | Adopt node-pg-migrate or drizzle-kit; baseline current schema; run migrations as an explicit deploy step. | M | Senior sets up, junior follows | Weeks 3–4 | BK-08
ISS-03 | Backups and restore untested / not configured | Critical | Data / DevOps | No backup automation in repo; only storage-admin-snapshot-merge.mjs and an admin JSON export endpoint; provider-side backup status unverified. | Student learning records are irreplaceable; the JSON-blob design makes corruption more likely, not less. | Any incident (bad deploy, provider issue, operator error) = permanent data loss. | Enable provider PITR/daily dumps; perform a scripted restore drill; document RPO ≤ 24h / RTO ≤ 4h. | S | DevOps / junior | Week 1 | BK-01
ISS-04 | CI gates nothing — push workflow only runs npm install | Critical | Workflow | .github/workflows/ci.yml: push job = checkout + npm install; type-check/tests/build only on manual dispatch flag. 109 unit test files + 60 e2e specs exist but never run automatically. | The safety harness exists but is disconnected; AI-agent-generated code lands unverified. | Regressions ship straight to production; test suite rots. | Run type-check + unit tests + build on every push/PR; block production deploys unless main is green. | S | Junior | Week 1 | BK-02
ISS-05 | No privacy baseline for a platform handling minors' data | Critical | Privacy / Legal | No privacy policy/consent flow in app; student context (names, attempts, work photos, voice) sent to Qwen/DeepSeek/EduHK/SimpleTex/Mathpix; optional xAPI LRS export; HK + mainland + US curricula imply PDPO/PIPL/COPPA-FERPA exposure. | Education platforms live on school and parent trust; legal regimes for minors are strict in all three target regions. | Regulatory exposure; a single parent complaint or school audit can end a pilot. | Minimum privacy pack: policy + consent, data-flow map, provider terms review, deletion/export path, LLM data minimization. | M | Product owner + senior | Start month 1; complete before real users | BK-24
ISS-06 | Sessions cannot be revoked | High | Security | lib/session.ts: stateless HMAC token, 7-day expiry; logout only clears the cookie; password change/reset does not invalidate existing tokens on other devices. | A leaked/stolen token stays valid for up to 7 days with no kill switch. | Account takeover persists even after the user resets their password. | Server-side session records (id + revoked flag); check on verify; revoke on password change; 'log out all devices'. | M | Junior with senior review | Month 2 | BK-14
ISS-07 | Anyone can self-register as teacher (and parent) | High | Security / Access control | app/api/auth/register/route.ts accepts role=teacher/parent from the public form; only admin is blocked. | Teacher role unlocks teacher-tier UI, AI tools and student-adjacent workflows; the trust boundary is undefined. | Strangers posing as teachers interacting with student data/flows on an education platform. | Invite code or admin approval for teacher signup; audit parent-child linking for verification. | S–M | Junior | Weeks 1–2 | BK-05
ISS-08 | Rate limiting is in-memory per serverless instance | High | Security / Cost | lib/server/rateLimit.ts: Map in module scope; Vercel runs many short-lived instances, so counters reset and are not shared. | Login brute-force and AI-cost abuse are effectively unthrottled in production despite the code existing. | Credential stuffing; surprise LLM bills; tutor abuse. | Durable limiter (Postgres or Upstash Redis) for auth + AI/OCR/speech routes, per-IP and per-user. | S–M | Junior | Weeks 1–2 | BK-06
ISS-09 | No error tracking, alerting, or structured logging | High | Observability | No Sentry/equivalent anywhere; 62 console.* statements; Vercel logs only, unwatched. | Production failures are invisible until a user reports them; debugging has no request context. | Extended outages; unreproducible bug reports; support burden on the owner. | Sentry client+server with release tags; uptime checks; request-ID logging in a shared API wrapper. | S | Junior | Week 1 | BK-03
ISS-10 | God modules mixing persistence, business rules and AI logic | High | Code quality | userStore.ts = 9,937 lines importing RAG packs, adaptive engine, LLM provider; ThreeDLabCanvas.tsx = 11,240 lines; ai-tutor/resolve route = 2,865 lines; repo ≈ 300k LoC. | Every change funnels through giant shared files: merge conflicts (esp. across 25 parallel AI agents), impossible code review, slow onboarding. | Change amplification: small features cause regressions in unrelated domains. | Split by domain behind interfaces as part of the strangler migration; mechanical moves protected by existing unit tests; no big-bang rewrite. | L | Senior guides, junior executes | Months 2–3 | BK-11, BK-12
ISS-11 | Inconsistent API validation and error handling | High | Backend | Hand-rolled typeof checks per route; no schema library; only ~7 of 160 routes use the shared JSON error boundary; error shapes vary. | Bad input can reach business logic; clients can't rely on error contracts; every new route reinvents the wheel. | Data-quality bugs and brittle frontend error handling accumulate. | zod schemas + shared withApiHandler wrapper (auth, validation, envelope, request-ID); top-20 routes first. | M | Junior | Weeks 3–8 | BK-09
ISS-12 | Secrets on disk in an AI-agent working tree | High | Security | 'All API Keys.docx' and .env.local in repo folder (gitignored but present); up to 25 autonomous agents operate in this tree per AGENTS.md; coordination logs reference key handoffs. | Any misbehaving agent or tool call can read and exfiltrate every provider credential; Word docs are uncontrolled key storage. | Provider account compromise; fraudulent LLM spend; data breach via provider APIs. | Rotate all keys; secrets only in Vercel env + password manager; delete key files; gitleaks pre-commit + CI + history scan. | S | Owner + junior | Week 1 | BK-04
ISS-13 | Deploy/rollback data hazard from write-on-read normalization | High | Deployment / Data | readPostgresDatabase triggers normalization write-backs of the full snapshot; during deploy overlap, old code can rewrite state produced by new code, silently dropping fields. | Code rollback (Vercel) is instant, but data written by newer code may be destroyed by older code still running. | Silent data regression after any rollback or slow rollout. | Remove write-on-read; make normalization an explicit versioned migration step; version the payload. | M | Senior | Month 2 | BK-07, BK-08
ISS-14 | No lint/format toolchain; bespoke fragile test pipeline | Medium | Workflow | No ESLint/Prettier in devDependencies; unit tests run via custom tsc → .tmp compile with symlinked '@' aliases across 4 tsconfigs. | Style drift and latent bugs go uncaught; test pipeline breaks mysteriously for newcomers. | Rising friction for every current and future contributor. | ESLint + Prettier + pre-commit; migrate unit tests to Vitest (native TS paths). | M | Junior | Month 2 | BK-16
ISS-15 | Frontend bundle weight and missing error boundaries | Medium | Frontend / UX | three + drei + phaser + framer-motion all present; client components (login page, roadmaps, forum) import from the 91 MB data/ tree; 8 loading.tsx but 0 error.tsx in app/. | Slow first loads on school hardware/networks; any render error white-screens the route with no recovery UI. | Teachers/students on old devices churn; demos fail badly on errors. | Bundle analysis + dynamic imports + per-route JS budgets; add error.tsx boundaries; audit data/ imports reaching clients. | M | Junior + designer | Month 2 | BK-13
ISS-16 | Repo hygiene and documentation drift | Medium | Workflow / Docs | 7,786 tracked files incl. QA evidence CSVs, video plans, coordination artifacts; 41 codex/* branches; README + live meta description still say 'HK Math Lab Template'; stray Users/, output/ dirs. | New engineers cannot tell product code from scratch output; branding confusion on the live site. | Onboarding takes weeks instead of days; stale branches hide unmerged work. | Archive non-product artifacts; prune branches; rewrite README/ARCHITECTURE/ONBOARDING; fix metadata. | M | Junior | Weeks 3–4 | BK-15, BK-18
ISS-17 | Experimental sync SQLite in request path; Node unpinned | Medium | Platform | node:sqlite DatabaseSync (experimental, synchronous) used for local/fallback storage; no engines field or .nvmrc; CI uses Node 24. | Sync DB calls block the event loop during large writes; environment drift between dev/CI/Vercel. | Mysterious latency locally; 'works on my machine' failures. | Pin Node via engines + .nvmrc; keep SQLite strictly local-dev; assert postgres provider at production boot. | S | Junior | Weeks 3–4 | BK-17
ISS-18 | CSRF protection relies solely on SameSite=Lax | Medium | Security | No CSRF tokens or Origin checks; session cookie is SameSite=Lax (blocks most cross-site POSTs on modern browsers). | Residual exposure on older browsers and any future GET-with-side-effects route. | Low-likelihood but cheap-to-fix account actions via CSRF. | Add Origin/Referer validation for mutations in the shared API wrapper; consider double-submit tokens later. | S | Junior | Month 2 | BK-09

## Roadmap
Phase | Window | Workstream | Key actions | Tickets | Owner | Success criteria / exit gate
1. Stabilization & risk reduction | Weeks 1–2 | Data safety | Verify prod Postgres; enable backups/PITR; run + document one restore drill | BK-01 | DevOps/JD | Restore drill passed; RPO/RTO written down
1. Stabilization & risk reduction | Weeks 1–2 | Delivery safety | CI gate: type-check + unit tests + build on every push/PR; deploys only from green main | BK-02 | JD | Red CI blocks merge and deploy
1. Stabilization & risk reduction | Weeks 1–2 | Visibility | Sentry client+server, release tags, uptime checks, alert channel | BK-03 | JD | Test error visible in Sentry; alert fires < 5 min
1. Stabilization & risk reduction | Weeks 1–2 | Secrets | Rotate all provider keys; delete All API Keys.docx; Vercel env + password manager; gitleaks | BK-04 | Owner+JD | Old keys revoked; scans green
1. Stabilization & risk reduction | Weeks 1–2 | Access control | Teacher registration behind invite code; parent-link audit | BK-05 | JD | Teacher signup w/o code → 403 (e2e-tested)
1. Stabilization & risk reduction | Weeks 1–2 | Abuse/cost | Durable rate limiting on auth + AI routes | BK-06 | JD | Limits hold across instances
1. Stabilization & risk reduction | Weeks 1–2 | Architecture guardrail | app_state freeze ADR: no new data into the blob | BK-07 | SE | ADR merged; PR checklist updated
2. Architecture cleanup & docs | Weeks 3–4 | Schema management | Migration framework adopted; baseline committed; DDL only via migrations | BK-08 | SE+JD | migrate up/down works on staging
2. Architecture cleanup & docs | Weeks 3–4 | API consistency | Shared withApiHandler (auth+zod+envelope+request-ID); convert top-20 routes | BK-09 | JD | Converted routes uniform; 400s carry field errors
2. Architecture cleanup & docs | Weeks 3–4 | Environments | Real staging: separate Vercel project + Postgres + seed; smoke suite per release | BK-10 | DevOps/JD | Staging green gate wired into deploy script
2. Architecture cleanup & docs | Weeks 3–4 | Docs & hygiene | README/ARCHITECTURE/ONBOARDING rewrite; repo artifact archive; branch prune; Node pinning | BK-15, BK-17, BK-18 | JD | New dev to running app < 1 hour; < 3,000 tracked files
3. Core refactoring & foundation | Month 2 | Data migration wave 1 | learning_events + lesson_progress, then messages/notices: dual-write → backfill → parity → cutover | BK-11, BK-12 | SE+JD | Parity ≥ 99.9%; reads switched; blob writes stopped for wave-1 domains
3. Core refactoring & foundation | Month 2 | Deploy/data safety | Remove write-on-read normalization; versioned payload | BK-07, BK-08 | SE | Rollback no longer mutates data
3. Core refactoring & foundation | Month 2 | Code structure | Split userStore.ts into lib/domains/* behind interfaces (mechanical, test-protected) | — | SE guides JD | No file > 1,500 lines in lib/server core; tests green
3. Core refactoring & foundation | Month 2 | Sessions | Server-side session records; revoke on password change; log-out-all | BK-14 | JD | Password change invalidates other devices (e2e)
3. Core refactoring & foundation | Month 2 | Tooling | ESLint+Prettier; Vitest migration; e2e nightly on staging | BK-16 | JD | npm test < 5 min; nightly report visible
3. Core refactoring & foundation | Month 2 | Frontend | Bundle analysis; lazy-load three/phaser; error.tsx everywhere; data/-import audit | BK-13 | JD+DS | Route budgets met; no white-screen on error
4. Hardening & controlled expansion | Month 3 | Data migration wave 2 | classes, enrollments, assignments, submissions to normalized tables | — | SE+JD | Same parity gate as wave 1
4. Hardening & controlled expansion | Month 3 | Privacy | Policy+consent, data-flow map, provider review, deletion/export, LLM minimization | BK-24 | PO+SE | Deletion request fulfilled in test; policy live
4. Hardening & controlled expansion | Month 3 | Performance | k6 classroom load test (200 students); fix top 3 bottlenecks | BK-19 | SE+JD | p95 attempt submit < 2s @ 200 users
4. Hardening & controlled expansion | Month 3 | Security | Headers+CSP report-only; Origin checks; npm audit triage; admin audit log | BK-21, BK-22 | JD | securityheaders.com ≥ A-; audit log queryable
4. Hardening & controlled expansion | Month 3 | AI/adaptive | AdaptiveEngine interface extraction + recommendation_log; budget guard hard caps | BK-20 | SE+JD | Recommendations logged with outcomes; overage cuts AI gracefully
4. Hardening & controlled expansion | Month 3 | Operations | Rollback/incident runbook + game day; restore drill #2; pilot 1–2 classrooms with daily monitoring | BK-23 | SE+JD+PO | Pilot runs 2 weeks with no Sev-1

## Backlog
ID | Title | Priority | Window | Owner | Description | Acceptance criteria
BK-01 | Enable and verify database backups | P0 | Weeks 1–2 | DevOps/JD | Enable automated backups/PITR on production Postgres; write restore-drill doc; perform one full restore to a scratch DB. | Backup schedule visible at provider; restore drill passed with row-count verification (app_state, auth_users, practice_attempts); RPO/RTO documented.
BK-02 | Make CI a real gate | P0 | Weeks 1–2 | JD | CI runs type-check, unit tests and next build on every push/PR; main is protected; deploy script requires green main. | Red CI blocks merge; production deploy refuses non-green main; pipeline < 15 min.
BK-03 | Error tracking + uptime alerts | P0 | Weeks 1–2 | JD | Sentry (server+client) with release tags/source maps; uptime checks on /, /login, one authed API; alerts to watched channel. | Test error appears in Sentry with release + route; downtime alert < 5 min in test.
BK-04 | Secret rotation + scanning | P0 | Weeks 1–2 | Owner+JD | Rotate all provider keys and session secret; delete 'All API Keys.docx'; secrets only in Vercel env + password manager; gitleaks pre-commit + CI + history scan. | Old keys revoked (verified non-working); no secret files in tree; gitleaks green.
BK-05 | Gate teacher registration; audit parent linking | P0 | Weeks 1–2 | JD | Invite code (admin-generated) required for role=teacher; parent-child links require verifiable code. | Teacher signup without code → 403 (e2e); parent cannot link arbitrary student; security test extended.
BK-06 | Durable rate limiting | P0 | Weeks 1–2 | JD | Postgres- or Upstash-backed limiter for login/register/reset + AI/OCR/speech routes; per-IP and per-user. | Limits enforced across instances; AI routes have per-user daily caps; 429s carry Retry-After.
BK-07 | app_state freeze ADR | P0 | Weeks 1–2 | SE | ADR: no new fields/domains in the JSON blob; document dual-write strangler recipe; update AGENTS.md/PR template. | ADR merged in docs/adr; PR checklist has the checkbox; agent instructions updated.
BK-08 | Migration framework | P1 | Weeks 3–4 | SE+JD | Adopt node-pg-migrate/drizzle-kit; baseline existing tables; all future DDL via committed migrations run as deploy step. | migrate up/down works locally + staging; runtime DDL removed or assertion-only.
BK-09 | Shared API handler (auth + zod + envelope) | P1 | Weeks 3–8 | JD | withApiHandler: session, role, zod validation, {code,error,requestId} envelope, Origin check on mutations, request-ID log. Convert top-20 routes. | Converted routes uniform; invalid body → 400 with field errors; wrapper unit-tested.
BK-10 | Staging environment + release smoke | P1 | Weeks 3–4 | DevOps/JD | Separate Vercel project + Postgres + seeded data; e2e smoke subset runs on staging for every release candidate. | Staging live with own DB; smoke green required by deploy script.
BK-11 | Strangler wave 1a: learning_events + lesson_progress | P2 | Month 2 | SE+JD | Tables via migration; dual-write; backfill from blob; shadow-read parity ≥ 1 week; switch reads; stop blob writes. Snapshot before cutover. | Parity ≥ 99.9%; reads from tables; blob no longer written for these domains; rollback path documented.
BK-12 | Strangler wave 1b: messages + notices | P2 | Month 2 | JD | Same dual-write/backfill/parity/cutover recipe for teacher/parent messages and notices. | Same gate as BK-11.
BK-13 | Frontend resilience + performance pass | P2 | Month 2 | JD+DS | error.tsx on all route groups; loading states verified; bundle analysis; dynamic-import three/phaser; remove data/ imports from client components; mobile check of 5 critical flows. | No white-screen on thrown error (e2e); login/dashboard/practice first-load JS under agreed budget; before/after documented.
BK-14 | Session revocation | P2 | Month 2 | JD (SE review) | sessions table (id, user, created, expires, revoked); token carries session id; revoke on password change/reset; log-out-all. | Password change invalidates other browser (e2e); revoked token → 401 within 60s.
BK-15 | Documentation reset | P1 | Weeks 3–4 | JD+PO | Rewrite README (real product/architecture/setup/env matrix); ARCHITECTURE.md; ONBOARDING.md; update site metadata off 'HK Math Lab Template'. | New dev to running local app < 1 hour from docs alone; live meta description updated.
BK-16 | Standard test tooling | P2 | Month 2 | JD | Migrate node:test suites to Vitest with native TS paths; delete tsc→.tmp symlink pipeline; wire to CI. | npm test < 5 min; bespoke compile scripts removed; CI uses Vitest.
BK-17 | Runtime pinning + storage assertion | P1 | Weeks 3–4 | JD | engines.node + .nvmrc matching Vercel; production boot asserts postgres provider + required env. | Wrong Node fails loudly; prod boot with sqlite provider fails with clear error.
BK-18 | Repo hygiene | P1 | Weeks 3–4 | JD | Archive coordination/ evidence, video-plan/, Users/, stray outputs; prune merged codex/* branches; document archive location. | Tracked files < 3,000; ≤ 5 active branches; archive documented.
BK-19 | Classroom load test | P3 | Month 3 | SE+JD | k6: 200 students login → practice → submit attempts + 10 teachers on analytics, against staging with prod-like volume. | p95 attempt submit < 2s; error rate < 1%; top 3 bottlenecks ticketed with evidence.
BK-20 | LLM budget guard | P2 | Month 2 | JD+PO | Central per-provider/day spend tracking (extend existing budget code); hard cap with graceful UX; 80% alert. | Simulated overage cuts AI routes only; owner alerted; caps per-env configurable.
BK-21 | Security headers + dependency audit | P3 | Month 3 | JD | Headers via next.config (frame-ancestors, nosniff, referrer-policy, permissions-policy) + CSP report-only; npm audit triage. | securityheaders.com ≥ A-; CSP reports logged; no unwaived high/critical deps.
BK-22 | Admin audit log | P3 | Month 3 | JD | audit_log table written by admin endpoints (export, provisioning, policy, bootstrap-admin) + auth events. | Admin export produces an audit row; queryable by user/date; retention documented.
BK-23 | Rollback + incident runbook | P3 | Month 3 | SE+JD | Document code rollback (Vercel), snapshot-before-cutover policy, migration down-path, incident first steps, comms template; run one game day. | Runbook in repo; simulated staging incident resolved following it.
BK-24 | Privacy pack | P3 | Month 3 (start earlier) | PO+SE | Policy + terms pages; registration consent; provider data-flow map + terms review; deletion/export path; LLM prompt minimization; verify media retention/encryption live. | Policy linked at register/login; test deletion fulfilled end-to-end; data-flow map in docs; jurisdiction sign-off.

## Readiness Checklist
Category | Item | Ticket | Status
Security | Teacher registration gated by invite/approval | BK-05 | Open
Security | Parent-child linking verified | BK-05 | Open
Security | Durable rate limiting on auth + AI routes | BK-06 | Open
Security | Session revocation + log-out-all | BK-14 | Open
Security | Keys rotated; secrets only in Vercel env; key files deleted | BK-04 | Open
Security | Secret scanning (gitleaks) in CI | BK-04 | Open
Security | Security headers + CSP report-only | BK-21 | Open
Security | Origin check on mutations | BK-09 | Open
Security | Admin audit log | BK-22 | Open
Data | Automated backups/PITR enabled | BK-01 | Open
Data | Restore drill passed + documented | BK-01 | Open
Data | Migration framework, baseline committed | BK-08 | Open
Data | app_state freeze enforced | BK-07 | Open
Data | Wave-1 domains on normalized tables | BK-11/12 | Open
Data | Prod boot asserts postgres provider | BK-17 | Open
Deployment | CI green required to merge + deploy | BK-02 | Open
Deployment | Staging env with seeded data | BK-10 | Open
Deployment | Release smoke suite on staging | BK-10 | Open
Deployment | Rollback runbook (code + data) | BK-23 | Open
Deployment | Node pinned; env matrix documented | BK-17/18 | Open
Testing | Unit tests + build on every PR | BK-02 | Open
Testing | 5 critical e2e flows green per release | BK-10 | Open
Testing | Load test passed (200 students, p95 < 2s) | BK-19 | Open
Monitoring | Sentry alerting to watched channel | BK-03 | Open
Monitoring | Uptime checks live | BK-03 | Open
Monitoring | LLM spend alarm + hard cap | BK-20 | Open
Documentation | README/ARCHITECTURE/ONBOARDING current | BK-15 | Open
Documentation | Incident runbook | BK-23 | Open
Documentation | Data-flow / privacy map | BK-24 | Open
UX | error.tsx boundaries everywhere | BK-13 | Open
UX | Loading states on data pages | BK-13 | Open
UX | Mobile check of 5 critical flows | BK-13 | Open
UX | Bilingual copy pass on core flows | BK-13 | Open
Privacy | Policy + terms published, linked at signup | BK-24 | Open
Privacy | Consent capture at registration | BK-24 | Open
Privacy | Provider inventory + terms reviewed | BK-24 | Open
Privacy | Deletion/export path works | BK-24 | Open
Privacy | LLM data minimization documented | BK-24 | Open